## Materials Master
Material ID | Material Name | Category | Unit | Unit Cost (PHP) | Reorder Level | Target Stock | Other Information
MAT-001 | Portland Cement 40kg | Cement | bag | 285 | 20 | 80 | Construction cement
MAT-002 | Ready-Mix Concrete 20MPa | Concrete | m³ | 4850 | 5 | 20 | Structural concrete
MAT-003 | 10mm Deformed Rebar | Steel | pc | 118 | 50 | 180 | Grade 60 reinforcing bar
MAT-004 | 12mm Deformed Rebar | Steel | pc | 165 | 45 | 160 | Grade 60 reinforcing bar
MAT-005 | 16mm Deformed Rebar | Steel | pc | 292 | 30 | 120 | Grade 60 reinforcing bar
MAT-006 | Marine Plywood 1/2in | Wood | sheet | 920 | 12 | 40 | 2440x1220mm
MAT-007 | Ordinary Plywood 1/4in | Wood | sheet | 510 | 15 | 50 | 2440x1220mm
MAT-008 | 2x2 Wood Furring | Wood | pc | 92 | 30 | 100 | 3m length
MAT-009 | 2x4 Wood Lumber | Wood | pc | 225 | 25 | 90 | 3m length
MAT-010 | Ceramic Floor Tile 60x60 | Finishes | box | 890 | 15 | 55 | 1.44m²/box
MAT-011 | Wall Tile 30x60 | Finishes | box | 760 | 12 | 45 | 1.44m²/box
MAT-012 | Tile Adhesive 25kg | Finishes | bag | 520 | 12 | 40 | Polymer-modified
MAT-013 | Grout 2kg | Finishes | bag | 165 | 10 | 35 | Cementitious grout
MAT-014 | Interior Latex Paint 4L | Paint | can | 690 | 8 | 30 | Low-VOC interior paint
MAT-015 | Exterior Paint 4L | Paint | can | 820 | 8 | 30 | Weather-resistant paint
MAT-016 | PVC Pipe 1/2in x 3m | Plumbing | pc | 145 | 20 | 70 | Schedule 40
MAT-017 | PVC Pipe 3/4in x 3m | Plumbing | pc | 185 | 18 | 60 | Schedule 40
MAT-018 | Electrical Wire THHN 2.0mm² | Electrical | m | 38 | 80 | 300 | Copper wire
MAT-019 | LED Downlight 9W | Electrical | pc | 185 | 15 | 60 | Warm white
MAT-020 | Stainless Cabinet Hinge | Hardware | pc | 42 | 30 | 120 | Soft-close hinge

## Suppliers
Supplier ID | Supplier Name | Contact Person | Contact Information | Address | Materials Supplied
SUP-001 | CebuBuild Supply Hub | Mia Santos | 0917-555-0101 | Mandaue City, Cebu | Cement, Steel, Hardware
SUP-002 | VisMin Timber & Panels | Carlo Reyes | 0917-555-0102 | Lapu-Lapu City, Cebu | Plywood, Lumber
SUP-003 | TileCraft Cebu | Angela Lim | 0917-555-0103 | Cebu City, Cebu | Tiles, Adhesives, Grout
SUP-004 | ColorPro Paint Center | Nico Tan | 0917-555-0104 | Talisay City, Cebu | Interior & Exterior Paint
SUP-005 | Cebu Pipe & Wire Depot | Jessa Cruz | 0917-555-0105 | Mandaue City, Cebu | PVC, Electrical Wire, Lighting
SUP-006 | Prime Hardware Traders | Mark Dela Cruz | 0917-555-0106 | Consolacion, Cebu | Cabinet Hardware & Tools

## Deliveries
Delivery ID | Delivery Date | Supplier ID | Material ID | Quantity Delivered | Purchase Order No. | Received By | Location
DEL-001 | 2026-08-01 | SUP-001 | MAT-001 | 50 | PO-260801 | Rowella | Warehouse A
DEL-002 | 2026-08-02 | SUP-001 | MAT-003 | 140 | PO-260802 | Rowella | Warehouse A
DEL-003 | 2026-08-03 | SUP-002 | MAT-006 | 30 | PO-260803 | Rowella | Warehouse B
DEL-004 | 2026-08-04 | SUP-003 | MAT-010 | 35 | PO-260804 | Rowella | Warehouse B
DEL-005 | 2026-08-05 | SUP-004 | MAT-014 | 22 | PO-260805 | Rowella | Warehouse C
DEL-006 | 2026-08-06 | SUP-005 | MAT-018 | 250 | PO-260806 | Rowella | Warehouse C
DEL-007 | 2026-08-07 | SUP-006 | MAT-020 | 90 | PO-260807 | Rowella | Warehouse A
DEL-008 | 2026-08-09 | SUP-001 | MAT-002 | 12 | PO-260809 | Rowella | Site Yard
DEL-009 | 2026-08-10 | SUP-001 | MAT-004 | 120 | PO-260810 | Rowella | Warehouse A
DEL-010 | 2026-08-11 | SUP-002 | MAT-008 | 75 | PO-260811 | Rowella | Warehouse B
DEL-011 | 2026-08-12 | SUP-003 | MAT-011 | 30 | PO-260812 | Rowella | Warehouse B
DEL-012 | 2026-08-13 | SUP-004 | MAT-015 | 20 | PO-260813 | Rowella | Warehouse C
DEL-013 | 2026-08-14 | SUP-005 | MAT-016 | 55 | PO-260814 | Rowella | Warehouse C
DEL-014 | 2026-08-15 | SUP-006 | MAT-019 | 50 | PO-260815 | Rowella | Warehouse A
DEL-015 | 2026-08-17 | SUP-001 | MAT-005 | 80 | PO-260817 | Rowella | Warehouse A
DEL-016 | 2026-08-18 | SUP-002 | MAT-007 | 45 | PO-260818 | Rowella | Warehouse B
DEL-017 | 2026-08-19 | SUP-003 | MAT-012 | 30 | PO-260819 | Rowella | Warehouse B
DEL-018 | 2026-08-20 | SUP-004 | MAT-013 | 25 | PO-260820 | Rowella | Warehouse C
DEL-019 | 2026-08-21 | SUP-005 | MAT-017 | 45 | PO-260821 | Rowella | Warehouse C
DEL-020 | 2026-08-22 | SUP-006 | MAT-009 | 70 | PO-260822 | Rowella | Warehouse A

## Issuance
Issuance ID | Issuance Date | Material ID | Quantity Issued | Project/Site | Requested By | Released By | Purpose
ISS-001 | 2026-08-10 | MAT-001 | 18 | J Tower Residence | Site Foreman | Warehouse Keeper | Masonry works
ISS-002 | 2026-08-11 | MAT-003 | 55 | Pacific Grand Lapu-Lapu | Site Foreman | Warehouse Keeper | Rebar installation
ISS-003 | 2026-08-12 | MAT-006 | 10 | Casa Mira Guadalupe | Site Foreman | Warehouse Keeper | Cabinet carcass
ISS-004 | 2026-08-13 | MAT-010 | 15 | Mivela Garden Residences | Site Foreman | Warehouse Keeper | Floor tiling
ISS-005 | 2026-08-14 | MAT-018 | 90 | Deca Banilad | Electrician | Warehouse Keeper | Electrical rough-in
ISS-006 | 2026-08-15 | MAT-020 | 35 | J Tower Residence | Cabinet Installer | Warehouse Keeper | Cabinet installation
ISS-007 | 2026-08-17 | MAT-004 | 40 | Boxhills Talisay | Site Foreman | Warehouse Keeper | Reinforcement works
ISS-008 | 2026-08-18 | MAT-014 | 10 | Pacific Grand Lapu-Lapu | Interior Designer | Warehouse Keeper | Interior painting
ISS-009 | 2026-08-19 | MAT-008 | 25 | Casa Mira Guadalupe | Carpenter | Warehouse Keeper | Ceiling framing
ISS-010 | 2026-08-20 | MAT-016 | 22 | Mivela Garden Residences | Plumber | Warehouse Keeper | Plumbing installation

## Returns
Return ID | Return Date | Material ID | Quantity Returned | Condition | Project/Site | Returned By | Received By | Reason for Return | Issuance ID
RET-001 | 2026-08-21 | MAT-001 | 4 | Good | J Tower Residence | Site Foreman | Warehouse Keeper | Excess material after masonry | ISS-001
RET-002 | 2026-08-22 | MAT-020 | 5 | Good | J Tower Residence | Cabinet Installer | Warehouse Keeper | Unused cabinet hinges | ISS-006
RET-003 | 2026-08-23 | MAT-018 | 12 | Good | Deca Banilad | Electrician | Warehouse Keeper | Remaining wire after rough-in | ISS-005

## Inventory Calculation
Material ID | Material Name | Delivered Qty | Issued Qty | Returned Qty | Available Qty | Unit Cost | Inventory Value | Reorder Level | Target Level | Status
MAT-001 | Portland Cement 40kg | 50 | 18 | 4 | 36 | 285 | 10260 | 20 | 80 | NORMAL
MAT-002 | Ready-Mix Concrete 20MPa | 12 | 0 | 0 | 12 | 4850 | 58200 | 5 | 20 | NORMAL
MAT-003 | 10mm Deformed Rebar | 140 | 55 | 0 | 85 | 118 | 10030 | 50 | 180 | NORMAL
MAT-004 | 12mm Deformed Rebar | 120 | 40 | 0 | 80 | 165 | 13200 | 45 | 160 | NORMAL
MAT-005 | 16mm Deformed Rebar | 80 | 0 | 0 | 80 | 292 | 23360 | 30 | 120 | NORMAL
MAT-006 | Marine Plywood 1/2in | 30 | 10 | 0 | 20 | 920 | 18400 | 12 | 40 | NORMAL
MAT-007 | Ordinary Plywood 1/4in | 45 | 0 | 0 | 45 | 510 | 22950 | 15 | 50 | NORMAL
MAT-008 | 2x2 Wood Furring | 75 | 25 | 0 | 50 | 92 | 4600 | 30 | 100 | NORMAL
MAT-009 | 2x4 Wood Lumber | 70 | 0 | 0 | 70 | 225 | 15750 | 25 | 90 | NORMAL
MAT-010 | Ceramic Floor Tile 60x60 | 35 | 15 | 0 | 20 | 890 | 17800 | 15 | 55 | NORMAL
MAT-011 | Wall Tile 30x60 | 30 | 0 | 0 | 30 | 760 | 22800 | 12 | 45 | NORMAL
MAT-012 | Tile Adhesive 25kg | 30 | 0 | 0 | 30 | 520 | 15600 | 12 | 40 | NORMAL
MAT-013 | Grout 2kg | 25 | 0 | 0 | 25 | 165 | 4125 | 10 | 35 | NORMAL
MAT-014 | Interior Latex Paint 4L | 22 | 10 | 0 | 12 | 690 | 8280 | 8 | 30 | NORMAL
MAT-015 | Exterior Paint 4L | 20 | 0 | 0 | 20 | 820 | 16400 | 8 | 30 | NORMAL
MAT-016 | PVC Pipe 1/2in x 3m | 55 | 22 | 0 | 33 | 145 | 4785 | 20 | 70 | NORMAL
MAT-017 | PVC Pipe 3/4in x 3m | 45 | 0 | 0 | 45 | 185 | 8325 | 18 | 60 | NORMAL
MAT-018 | Electrical Wire THHN 2.0mm² | 250 | 90 | 12 | 172 | 38 | 6536 | 80 | 300 | NORMAL
MAT-019 | LED Downlight 9W | 50 | 0 | 0 | 50 | 185 | 9250 | 15 | 60 | NORMAL
MAT-020 | Stainless Cabinet Hinge | 90 | 35 | 5 | 60 | 42 | 2520 | 30 | 120 | NORMAL